## Introduction
STRATEGIC PLANNING IMPLEMENTATION
The Strategic Plan Implementation Committee is an Ad Hoc Committee of the College of Design, Construction and Planning, reporting to the Dean and coordinating with the Faculty Council. The Committee is charged with furthering the implementation of the current DCP Strategic Plan, dated February 28, 2018.
Fall 2021 DCP Strategic Plan Implementation Committee:
ARC B. Walters, Chair
CM I. Flood
SLAP C. Silver
IND J. Meneely
Dean’s Office M. Portillo, ex-Officio
Introduction
In 2018 and 2019, the Strategic Plan Implementation Committee worked on translating the DCP Strategic Plan into a series of “enabling actions.” Individuals were then assigned responsibility for monitoring progress on these actions, and reporting back with progress towards completing the enabling actions that advance the plan. The following “champions” have been identified for plan implementation:
01. Governance, Equity, and Inclusion – Jeff Carney (Faculty Council Chair)
02. Education – Abdol Chini + Meg Portillo
03. Research and Creative Scholarship – Meg Portillo
04. Revenue Generation - Kutonya Sowell + Seth Watts
05. Facilities – Abdol Chini
06. Community Building and Culture (People) – Jeff Carney (Faculty Council Chair) + Joey Mazzaferro
07. Outreach – Seth Watts
08. Sustainability – Bahar Armaghani
09. International Education – Michael Kung
Instructions for Using this Implementation Document
This worksheet includes a total of ten tabs. Following this introductory tab, there are nine tabs/sheets corresponding to the nine sections of the plan listed above. When you select one of these tabs, the sheet will open and you will see a series of six columns, as follows:
A. Goals
B. Objectives
C. Enabling Actions (no more than 3-4 for each Objective)
D. Responsible Person or Group
E. Status (select one option from the pull-down menu: Not Started, In Progress, Completed, Not Essential)
F. Status Notes (50 word maximum)
We are asking all champions to provide a Status (Column E) and Status Notes (Column F) for each of the Enabling Actions listed. Where updates have been provided in the past, those should be visible along with the date that the status was updated.

## 01 Governance
01. GOVERNANCE, EQUITY AND INCLUSION
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Governance, Equity and Inclusion: The strength of shared governance is that it recognizes and respects the unique contributions of each individual as well as the recognized governance groups participating in the process. |  |  | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | -
1.1 Promote a culture of openness throughout the College, maximizing transparency and mutual respect. | 1.1.1 Communicate the rationale for decision-making processes and priorities. | 1.1.1.1 Explicitly reference the College’s strategic plan as the basis for college priorities. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress
|  | 1.1.1.2 Build upon my.dcp to create a centralized intra-College resource of relevant policies and procedures from the College and University (online college "handbook"). | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | My.DCP is operational and has had updates posted on it. Need to ensure consistency in its use.
|  | 1.1.1.3 Provide training and follow-up to support the use of the strategic plan, the handbook, and specific policies and procedures. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Not Essential | Unclear what the intent here is.
| 1.1.2 Clearly define decision-making roles and the relative influence of participants. | 1.1.2.1 For each major decision-making process, event, and committee formation, the leaders/chairs should explain the roles and relative influence of participants. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | Faculty Council is reviewing committee structure and chairs will regularly communicate about their activities.
| 1.1.3 Convey open information in a timely manner to appropriate faculty, staff, students and other stakeholders. | 1.1.3.1 Develop College communications plan to ensure faculty, staff, and students to stay apprised of important college decisions and events. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | Communications Team has developed a Marketing & Communications Plan that will be posted on My.DCP once approved.
| 1.1.4 Maintain and establish open lines of communication with fair avenues for people within the College to express concerns and issues. | 1.1.4.1 Promote existing channels of representation and communication, such as the Faculty Council. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | Dean and Faculty Council Chair now meet every 6 weeks. Faculty Council members encouraged to raise issues from their units at Council meetings.
|  | 1.1.4.2 Establish a formal college grievance process, which links to unit grievance processes. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Completed | College will follow UF grievance process.
1.2 Ensure involvement and participation of all faculty, staff, students and other stakeholders when decisions have significant impacts on departments/schools, or other DCP units. | 1.2.1 Encourage participation of all stakeholders in key decision-making processes. | 1.2.1.1 Unit and committee leaders institute methods for broad stakeholder participation throughout the various decision-making processes. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | Dean and Faculty Council Chair to remind chairs/directors to consult broadly before making key decisions. Ad hoc Committes involving stakeholders to be set up as needed.
| 1.2.2 Engage in creative problem solving to incorporate diverse perspectives and minority viewpoints. | 1.2.2.1 The college communications plan above should promote specific methods explicitly designed for communicating and respecting diverse perspectives and minority viewpoints. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | Draft Communications plan and DCP DEI plan both address this.
|  | 1.2.2.2 Offer a college-wide workshop, preferably led by an outside-DCP expert, on skills for collaborative problem-solving, negotiation, and cross-cultural/interdisciplinary communication. The workshop should be open to all but at a minimum involved unit and committee chairs. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Not Started | Dean and Faculty Council Chair to identify appropriate provider for this workshop.
| 1.2.3 Require the highest standards of ethical conduct for all members of the College. | 1.2.3.1 Training to support the college strategic plan and handbook, and other policy tools (e.g., the college communications plan), should explicitly incorporate ethics. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Not Started | Unclear what training is required/available for this.
|  | 1.2.3.2 College and unit leadership should regularly monitor activities and immediately address ethical breaches, with responses fitting the magnitude of the problem. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Completed | Unit leaders routinely monitor and deal with these.
|  | 1.2.3.3 Committees and other organizational entities designed to provide checks and balances of power should discuss their roles, importance, and relation to procedures (e.g., grievance processes). | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | In Progress | Faculty Council has reviewed DCP Committees and is clarifying their roles within the Constitution.
1.3 Work for College cohesion while maintaining the individual integrity of each academic unit. | 1.3.1 Work to build on the strengths of each unit/program to effectively contribute to the College agenda. | 1.3.1.1 Promote the concept of “One DCP” and establish initiatives that promote this amongst students, faculty, staff and alumni. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Completed | Several collaborative initiatives now established at student, staff, faculty and alumni levels. New ideas always welcome.
| 1.3.2 Establish consistent and effective policies, processes, resources and priorities at the College level. | See above, especially the college handbook. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | - | Unclear what the intent here is.
1.4 Advocate the best interests of the College in relation to other colleges, the university and the public. |  | 1.4.1.1 Strengthen existing channels, resources, and procedures (e.g., website updates and social media) to externally communicate DCP contributions. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney | Completed | College external communications significantly revamped. Dean now involved in numerous UF-level and external committees.
|  | 1.4.1.2 Continue and strengthen efforts to maintain contact with alumni, as key stakeholders in the college and potential partners for initiatives. | Dean, in consultation with Faculty Council Chair C.Anumba + J.Carney - SETH | Completed | DCP Advancement Team continuing to reach out to alumni all over the country. Unit advisory boards helping with this.

## 02 Education
02. EDUCATION
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Education: Excellence in teaching is a cornerstone of the College, which requires that we provide our students access to full and rich humanitarian traditions of higher education, technical prowess, design speculations and innovations, multi- disciplinary professional alliances, and focused research efforts that will frame the future of the built and natural environments |  |  | DCP Associate Deans for Undergraduate and Graduate Education A.Chini + M.Portillo, in consultation with Z.Peng | -
2.1 Ensure the continual advancement of undergraduate teaching and learning, in alignment with university goals | 2.1.1. Improve student recruitment efforts, student diversity, retention rates, and overall on-time graduation numbers. | 2.1.1.1. Have an Incoming Student Research Forum for undergraduate students, not just Preview. | DCP Associate Dean for Undergraduate Education A.Chini | -
|  | 2.1.1.2. DCP students and faculty should attend and/or present research at the UF Fall Undergraduate Research Expo . | DCP Associate Dean for Undergraduate Education A.Chini | Completed
|  | 2.1.1.3. More FaceTime at UF research events. | DCP Associate Dean for Undergraduate Education A.Chini | -
| 2.1.2. Distribute faculty lines and graduate teaching assistantships across units/programs to ensure that they are based on need as well as past success. | 2.1.2.1. Continuously evaluate undergraduate teaching resources by identifying areas of strength and weakness within each unit. | DCP Associate Dean for Undergraduate Education A.Chini | -
| 2.1.3. Invest in teaching excellence at all levels of undergraduate education. | 2.1.3.1. Provide more discipline-specific teaching and training assistance to faculty. Start a “DCP First Year Faculty Academy.” | DCP Associate Dean for Undergraduate Education A.Chini | -
|  | 2.1.3.2. Provide teaching refresher classes every 3-5 years. | DCP Associate Dean for Undergraduate Education A.Chini | -
| 2.1.4. Strategically expand curricular offerings without incurring an excessive increase in workloads or demand on current resources. | 2.1.4.1. Identify strategic areas for curricular expansion to increase teaching outreach. | DCP Associate Dean for Undergraduate Education A.Chini | -
2.2 Ensure the continual advancement of current graduate programs | 2.2.1. Improve recruitment efforts, retention rates, and overall graduation numbers of graduate students. | 2.2.1.1. Develop and monitor progress towards achieving specific goals for enrollment, retention rates, and graduation numbers for all DCP graduate programs. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
|  | 2.2.1.2. Develop benchmarks based on peer institutions. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
|  | 2.2.1.3. Develop dual-degree programs with other units, including 4+1, 4+1+1, 4+2 program options, amongst others. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
| 2.2.2. Expand teaching and research opportunities available for Master's and Ph.D. students | 2.2.2.1. Increase productivity of faculty in terms of writing proposals and receiving grants. Develop specific, targeted workshops for faculty and staff support for funded research. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
|  | 2.2.2.2. Shift development/fundraising focus to increase opportunities for graduate fellowships and stipends. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
|  | 2.2.2.3. PhD transition to more direct teaching after guided teaching introduction. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
| 2.2.3. Increase the profile, ranking and visibility of the graduate programs within the College. | 2.2.3.1. Invest in public relations to improve rankings. | DCP Associate Dean for Graduate Education M.Portillo | -
|  | 2.2.3.2. Invest in research production within matrix for Academic Analytics (need specific information from UF). | DCP Associate Dean for Graduate Education M.Portillo | -
|  | 2.2.3.3. Support, encourage, and incentivize collaborations with high-profile programs at other institutions. | DCP Associate Dean for Graduate Education M.Portillo | -
| 2.2.4. Invest in teaching excellence at all levels of graduate education. | 2.2.4.1. Bring in outside expertise. Collaborate on research with global industry partners. Integrate research into coursework. | DCP Associate Dean for Graduate Education M.Portillo | -
| 2.2.5. Strategically expand curricular offerings without incurring an excessive increase in workloads or demand on current resources. | 2.2.5.1 Identify strategic areas for curricular expansion to increase teaching outreach. Coursework to appeal across DCP and campus. Create cross-listed courses where possible. | DCP Associate Dean for Graduate Education M.Portillo | -
|  | 2.2.5.2 Create minors for the PhD program. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
| 2.2.6. Create new programs as needed to expand opportunities for graduate students. | 2.2.6.1. Create new programs as needed to expand opportunities for graduate students. | DCP Associate Dean for Graduate Education M.Portillo, in consultation with Z.Peng | -
2.3 Enhance interdisciplinary collaboration | 2.3.1. Increase interdisciplinary collaboration through course offerings that can attract interests across the UF community. | 2.3.1.1. Identify, develop, and introduce interdisciplinary courses. Introduce DCP studio courses to UF campus community. | DCP Associate Dean for Undergraduate Education A.Chini, in consultation with Unit Directors and Faculty | -
|  | 2.3.1.2. Create new minors in DCP areas of study. | DCP Associate Dean for Undergraduate Education A.Chini, in consultation with Unit Directors and Faculty | -

## 03 Research
03. RESEARCH AND CREATIVE SCHOLARSHIP
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Research and Creative Scholarship: The depth and breadth of influence of the College is perhaps best reflected in the rich and diverse scholarship and research of our faculty. This work is instrumental in advancing the College’s visibility and profile as the preeminent college for all aspects pertaining to the built and natural environments. We support the ambition to have the research and scholarly efforts of the faculty and units enhanced, accelerated and disseminated across national and international venues. |  |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
3.1 Engage faculty, staff and students in approved, nationally recognized and appropriately funded research, training and outreach centers consistent with the College mission and reflecting the expertise of its faculty. | 3.1.1 Increase the number and value of proposals submitted by College faculty, with a view to at least doubling research awards within 3 years. | 3.1.1.1. Research mentorship: Put CO-PI and doctoral students on grants, as approriate. Provide accessibility to NSF workshops. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | In Progress | 2020-07-13: Baseline developed. Discuss with college leadership. Align with UF Dept practices.
|  | 3.1.1.2. Create a voluntary pre-review panel for reviewing large grant proposals before submission to increase awards. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Not Started | 2020-07-13: Develop cache of senior researchers to initiate ??, see examples. Align with UF best practices
|  | 3.1.1.3. Strengthen college-wide research visibility and impact through a signature line of inquiry that builds on extant strengths: Florida Institute for Built Environment Resilience (FIBER) | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: Formally launched FIBER on March 20, 2019; completed faculty's postdoctoral hiring 2019 (7 faculty; 4 post docs) with expertise representing the core disciplines in DCP; aquired space within the city of Gainesville's Catalyst building to house the institute.
|  | 3.1.1.4. Create a baseline of research productivity with an agreed upon time period. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: Compile a college wide research productivity overview for annual state of the college dean's report and SACS accredition
|  | 3.1.1.5. Units to develop a 3 year plan to increase research productivity and creative scholarship. Consider having faculty prepare personal research plans. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Not Started | 2020-07-13: Assign report formed and deadline; Consider including centers
| 3.1.2 Ensure that new faculty hires have the capacity to strengthen the research output of the College. | Increase mentoring and communicating clear research expectations. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: Offer regularly scheduled presentations and forums to discuss and gain skills in research and creative scholarship. Align mentoring with UF best practices
| 3.1.3 Integrate centers in research-oriented events, such as the annual College research symposium. | Regularly connect with Center Directors on ways to disseminate their research | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: Since 2017 biannual meetings with center leaders/directors has occurred and the collete research symposium included new seminars and future center research
| 3.1.4 Enhance interdisciplinary and transdisciplinary research through selective engagement with other campus units. | 3.1.4.1. Develop research question or questions that require inter/transdisciplinary engagement. Identify units and/or individuals with relevant expertise and reach out to them to develop interdisciplinary teams. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | - | 2020-07-13: FIBER is addressing this. Capture activity of the unit level.
| 3.1.5 Strengthen the College research seminar program. | 3.1.5.1. Require Ph.D. students to regularly present their research work through seminars open to students, faculty, and staff. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: Doctoral students regularly share their research in the DCP seminar series, participate in the annual poster seminar in the
| 3.1.6 Strengthen research infrastructure. | 3.1.6.1 Have Units/Centers develop a plan to facilitate research engagement by supporting pilot projects and studies leading to ongoing productivity and external funding. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Not Started | 2020-07-13: DCP Research Symposium and the college and commuity of its doctoral defenses
|  | 3.1.6.2 Identify appropriate contacts with program directors at federal agencies and private foundations that may be interested in sponsoring research related to planning, design and construction. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
|  | 3.1.6.3 Increase faculty awareness and use of the PIVOT funding repository that includes specific programs objectives, deadlines etc. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: In January 2020, Assistant Vice President Research presented on PIVOT as part of a session on grantsmanship. The presentation was distributed to the faculty at large.
3.2 Secure and sustain a source of funding to seed new research initiatives and to complete ongoing projects. | 3.2.1 Establish seed grant programs to help develop exploratory research in preparation for grant applications. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed | 2020-07-13: Offered college-wide seed grant funding from 2017-19 increased new faculty startup funding with contribution to the Office of Research
| 3.2.2 Incorporate funding of faculty research within priorities of development activities. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | In Progress | 2020-07-13: More development funding will be needed to support new projects
| 3.2.3 Establish funding for faculty travel to national funding agencies and foundations. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | - | 2020-07-13: Offered in three cycles of college-wide funding
| 3.2.4 Explore alternative research funding streams. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
| 3.2.5 Hire or designate a specialist in grant applications and support. | 3.2.5.1. Develop job description collaboratively to engage all units and to address the wide diversity of funded research needed within the College. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | In Progress | 2020-07-13: Have increased communication and formalized policies across staff who support new-and-past awards. DCP has doubled grant staff support
3.3 Identify areas of clustered research interest in the College to create synergies for individual faculty and faculty affiliated with research centers. | 3.3.1 Maintain a clear description of centers and areas of research interest on the College website, and identify the faculty participating in each. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | In Progress | 2020-07-13: Will address this in the spring/summer of 2020 ongoing
| 3.3.2 Continue the annual College research symposium. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | Completed
3.4 Grow research funding from year to year, with the aim of significantly increasing research expenditures by 2022. | 3.4.1 Increase the number and value of proposals submitted by College faculty. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
| 3.4.2 Encourage the formation of multi-disciplinary teams that can go after larger grants. |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
| 3.4.3 Support faculty in diversifying the sources of funding for research. | 3.4.3.2 Benchmark innovative research partnerships--within the Units’ peer programs—to begin expanding DCP ongoing interdisciplinary involvement. | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
3.5 Develop publication expectations |  |  | Associate Dean for Research and Strategic Initiatives M.Portillo, in consultation with Unit Chairs/Directors + Center Directors | -
Notes:
1) Generate ideas and strategies to build from small to larger funded proposals, research, grants (don't downplay small grants for beginning researcher)
2) Create a more targeted listing of grants well in advance of deadline

## 04 Revenue
04. REVENUE GENERATION
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Revenue Generation: Adequate funding assembled from multiple sources is essential for our College to fulfill its mission. We recognize that the needs of our diverse programs vary due to national and international competition, the College’s available infrastructure, and access to outside funding sources. We seek sufficient funds to offer the highest quality degree programs, and research initiatives, recognizing that College approval constitutes a commitment to partner in securing the resources needed to achieve success. |  |  | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | -
PRIORITY GOAL (Created by combining 4.3-4.4): Focus on improving DCP programs by infusing them with funds, including discretionary funds, research dollars and private corpoate/foundation gifts, as appropriate |  | DEVELOPMENT: 1) Set realistic goals with the development team, based on university campaign goals, and make fundraising a priority among all faculty and staff; 2) Faculty and staff to increase communication with development team, with each unit to develop a catalog of accomplishments and a list of specific needs (e.g., $3k for conference travel for students). Units will also invite development team members to faculty meetings, share contacts with them, etc. RESEARCH: 1) Identify and implement creative ways to fund students as research assistants (e.g., DCP and units split cost); 2) create endowed positions; 3) Continue internal DCP research seed grant program initiatives. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: For #3) The DCP Research Seed Grant Program initiative is complete. Consider removing the wording related to seed grant or use revised language in red.
4.1 Secure the College’s fair share of state funding. | 4.1.1 The new UF budget model links student credit hour (SCH) production and tuition to provide baseline state funding for academic programs. |  | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | Completed | 2020-02-24: The University has transitioned to the new budget model and the college currently recieves the annual state revenue based on this model.
| 4.1.2 A balanced budget is required at the College level based on SCH generation, program costs and target enrollments. |  | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: The college currently balances the state budget beginning with a zero dollar balance and maintains a positive balance for the entire fiscal year. Departments request their budgets based on their departmental needs.
| 4.1.3 In addition to faculty and staff salaries, basic operating budgets are required for all degree programs and administrative oversight. |  | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | Completed | 2020-02-24: Departmental budget requests are submitted each year, budgets are allocated based on available funds after salaries.
| 4.1.4 Establish strategic and discretionary funds for unit directors and chairs. | 4.1.4.1. Development team to increase communication with units/faculty to ensure that they know of specific needs and accomplishments. Identify concrete examples of what units need (e.g., $3,000 for student travel to conferences). | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | Completed | 2020-02-24: Each unit/program has a memorandum of giving which the Development team uses. (CJA)
|  | 4.1.4.2 Offer seed grants to units for specific strategic programs or activities. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: Seed grants are allocated on an as need basis when funds are available. (CJA)
| 4.1.5 Address the problem of salary compression of faculty members. | 4.1.5.1 Recommend this be addressed at the university level. Note: Also addressed in Culture domain. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: University - level issues. Not something the College can address itself. 1st Round completed in 2017. (CJA)
4.2 Support existing and develop new off-book programs that, once established, cover direct program costs while also contributing a strategic revenue source for on-book programs. | 4.2.1. Conduct a review of existing off-book programs to establish their financial health, viability and relevance. | 4.2.1.1. Conduct a review of all existing off-book programs to establish their financial health, viability, and relevance. Off-book programs can be classified as revenue-neutral or revenue-generating. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | Not Started | 2020-02-24: Annual budgets are submitted each year and most of the program administrators meet with the Dean and Budget Director but a full program review for each of program has not been completed.
| 4.2.2. Identify opportunities for new off-book programs in consultation with academic program advisory boards. | 4.2.2.1. Off-book programs can be quite lucrative, but they can also be a huge distraction. Off-book programs not lucrative or self-sustaining should be placed under review to under go an improvment plan. Focus only should also be on new offers with high revenue-generating potential. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | Not Started | 2020-02-24: If after a completed review it is found a program is not lucrative or self sustaining, there can be a review process to assist with improvement. This wording can be added into 4.2.2.1 reviewed for improved.
| 4.2.3. Provide strong and efficient administrative and logistic support to all off-book programs. |  | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: Each program has their own administrative support that is supported by the program's revenue. Develop means where the administrators can meet regularly to discuss processes and procedures.
4.3 Develop a robust funded research portfolio for the College using incentives and policies to encourage faculty participation. | 4.3.1 Implement incentives and targets for the use of direct and indirect costs to support: a. Master's and doctoral students b. Summer salaries for faculty c. Soft money for researchers including post docs d. Staff positions e. Faculty, staff and student travel | 4.3.1.1 Identify and implement creative ways to fund students (e.g., unit covers 1/2 and DCP covers 1/2 of the cost). NOTE: the cost of funding students is a barrier | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: Please note: College does not generate enough IDC to do any of the objectives under 4.3.1. Dean in discussion with Grad School about this. (CJA)
|  | 4.3.1.2 Create endowed positions | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2021-10-28: Development Team continuing to cultivate donors to help support and fund endowed positions (STW)
|  | 4.3.1.3 Continue research seed grant program | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: Seed funds from Dean's startup now exhausted. Program will continue if/when new funds are available. (CJA)
|  | 4.3.1.4 Develop incentives (e.g., course release) for faculty to write grant proposals. Coordinate with baseline measures and research plans as a part of Goal 3.1. NOTE: See enabling actions for Goal 3 - Research and Creative Scholarship | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: Dr. Portillo has developed a series of workshops that target professional development - one in the area of research. The University also offers various workshops and this information is sent out on the DCP Faculty listserv.
4.4. Continue to cultivate and pursue private and corporate/foundation gifts that: a. Grow the College’s endowment year on year, with a view to increasing it by 50% by 2020. b. Suport the College’s strategic initiatives. c. Strengthen academic units and their individual initiatives. d. Develop linkage between advisory committees and strategic initiatives. e. Further research links and initiatives with industry. f. Enhance and expand the College’s facilities. |  | 4.4.1.1. Revise 4.4a goal. As stated, it is probably unrealistic given our facilities needs. Develop realistic goals with the development team that are driven by UF campaign goals | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2021-10-28: College has raised $48M as part of Go Greater Campaign and $14.5M for facilties. (STW)
|  | 4.4.4.2. Make fundraising a priority for all faculty and staff. Faculty need to build trust with the development team, invite them to a faculty meeting and connect them with their key contacts | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2021-10-28: Engaging more faculty in the development process. NYC is an example of engaging Directors and students in the development process (STW)
|  | 4.4.4.3. Communicate the College's strategic initiatives with the advisory committees. Consider sharing matrices with committees annually or providing a brief summary of the strategic initiatives they may help us achieve. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2021-10-28: DCP Leadership Summit is used each to to communicate these strategic initiatives to advisory boards and receive their feedback. (STW)

## 05 Facilities
05. FACILITIES
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Facilities: Our College is unique on the university campus as it is the nexus of so many of the different disciplines that examine, analyze, understand, review, design and construct our built and natural environments. As such, we need to ensure that our facilities meet the immediate needs for teaching and research, anticipate future needs and ambitions within the units, between units, within the College as a whole, and aspire to embody and reflect the best vision of our collected professions. |  |  | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | -
5.1. Improve our existing instructional facilities to ensure that our students and faculty have the best spaces in which to learn, to conduct research, to experiment, to collaborate, and to advance the strategic objectives of each unit and the College as a whole. | 5.1.1. Perform a comprehensive inventory and evaluation of the College’s instructional infrastructure. | 5.1.1.1. DCP Facilities Committee to develop a survey for inventoring facilities categorizing based on priorities: 1) Safety; 2) Function/use; 3) Quality; 4) Strategy. Each unit needs to create a committee to administer survey | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
| 5.1.2. Identify the usage and distribution of spaces and physical resources within and between units | 5.1.2.1 Request from each unit/program a list of current faculty offices and resources, any existing shortfalls, and specific and anticipated future faculty needs. Create unit-level committee that meets w/ DCP Facilities committee to report | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
| 5.1.3. Identify areas of strength and shortfalls, grounded in needs as well as opportunities. | 5.1.3.1. Survey faculty, students, all users to evaluate strengths & shortcomings. Compare outcomes from 5.1.1 and 5.1.2. | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
| 5.1.4. Identify potential spaces to become laboratories for making and enhancing collaborative work. | 5.1.4.1. outcome of 5.1.2 + 5.1.3. | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
5.2. Develop an immediate vision for improvements and growth needs of the College, while also working in close consultation with each individual unit to ensure that the integrity and needs of all are properly addressed. | 5.2.1. With UF Facilities Services, identify immediate problem areas, prioritize and, with faculty and staff of affected units and the College, develop strategies. | 5.2.1.1. Prioritize based on: 1) Safety; 2) Function/use; 3) Quality; 4) Strategy. | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
| 5.2.2. Ensure transparency about how College facilities are being used, distribution strategies, anticipated needs and accompanying planning strategies. | 5.2.2.1. Decisions should be set based on sqft for each students; Also encourage potential overlaps studio/collaboration (could be shared) | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
| 5.2.3. Develop an open dialogue with the entire College community to ensure that investments into the physical resources target a shared vision. | 5.2.3.1. Provide more workshops to get input from end users. | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed
5.3. Develop a long-term vision of the future needs of the College and accompanying strategy for development efforts and capital campaigns to support those needs. | 5.3.1. Undertake a study of the long-term needs of the College and each academic unit. | 5.3.1.1. Formulate a road map for realizing the College’s long-term vision. | Associate Dean for Facilities A.Chini, in consultation with Facilities Committee (including Faculty/Staff, Students, and Alumni) | Completed

## 06 Community
06. COMMUNITY BUILDING AND CULTURE (PEOPLE)
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Community Building and Culture: We believe that the single greatest resource of our College is its people. Administrators, current and emeritus faculty, staff, alumni, and students at all levels form the heart of the DCP community, and our goals, vision and aspirations for preeminence must be anchored to the collective strengths and specific contributions that the College brings to the University. |  |  | Dean, in consultation with Unit Chairs/Directors, Faculty Council, and DCP Communications Staff C.Anumba | -
6.1 Enrich the relationships and experience of our students within and across majors and units. | 6.1.1 Cultivate a sense of mutual respect within the student body by investing in existing student groups. | 6.1.1.1 Survey all student groups in DCP to determine their memberships, missions, and activities, and future needs. | DCP Communications Staff J.Mazzaferro | Not Started | 2021-11-17: This is the first I've heard of this. Will need to secure a list of groups and develop a survey.
| 6.1.2 Identify and develop opportunities for collaborative student projects and experiences within and beyond the classroom. | Reference 2.3. "Interdisciplinary Collaboration" | n/a | -
6.2 Recognize, value and manage faculty positions, roles and responsibilities within the College. | 6.2.1 Ensure equitable budgeting, compensation, and benefits to incentize faculty members | Reference 4.1.4. and 4.1.5. "Faculty Compensation" | n/a | -
| 6.2.2 Ensure that the units set clear, reasonable, and fair work expectations and priorities for promotion and tenure. | 6.2.2.1 Create a College working group to better formulate and communicate expectations for tenure and promotion, and provide mentorship. | Faculty Council Chair, in consultation with Dean, Unit Chairs/Directors J.Carney | -
|  | 6.2.2.2 Create a College system for tracking metrics for research, teaching, service, and professional impacts. | Dean, in consultation with Unit Chairs/Directors C.Anumba | -
| 6.2.3 Ensure that college expectations for promotion and tenure reflect an appreciation for the distinctions between units. | 6.2.3.1 Review the college promotion and tenure guidelines with this in mind. | Faculty Council Chair, in consultation with Dean, Unit Chairs/Directors J.Carney | -
| 6.2.4 Recognize and reward faculty excellence. | 6.2.4.1 Recognize faculty for outstanding performance that supports the college strategic plan, through existing and new awards. | Dean, in consultation with Unit Chairs/Directors C.Anumba (+ M.Kung) | -
| 6.2.5 Reinforce teamwork and delegation of duties and responsibilities. | 6.2.5.1 Promote and recognize teamwork and its accomplishments, through existing and new awards. | Dean, in consultation with Unit Chairs/Directors C.Anumba (+ M.Kung) | -
6.3 Provide adequate support to faculty to improve their teaching, research and service effectiveness at all levels and improve morale | 6.3.1 Provide adequate support for professional development and training | 6.3.1.1 Secure funds to support faculty travel for conferences. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: College uses unrestricted funds to support travel requests for faculty.
| 6.3.2 Provide adequate support for research activities. | 6.3.2.1 Support research grant-writing and training. Note: Additional enabling actions are identified under the Research and Creative Scholarship domain. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | In Progress | 2020-02-24: The University offers grant related workshops; this information is sent to the DCP Faculty listserv as it is received.
|  | 6.3.2.2 Increase funding for undergraduate and graduate research support. See also Revenue Generation and Research and Creative Scholarship matrices. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | -
| 6.3.3 Provide adequate support for teaching activities. | 6.3.3.1 Increase funding for undergraduate and graduate teaching support. | Dean, in consultation with DCP Budget Director + Director of Development C.Anumba (+ K.Sowell + S.Watts) | -
6.4 Strengthen College cohesiveness and continuity. | 6.4.1 Support mutally beneficial relationships within units, across units and with the Dean’s Office. | 6.4.1.1 Establish collaborative sessions to identify needs and opportunities for units to work together. | Dean, in consultation with Unit Chairs/Directors C.Anumba (+ M.Kung) | Completed | 2020-04-08: M.Kung Status
| 6.4.2 Raise awareness of the different roles and strengths of the different units, centers, and groups within the College. | 6.4.2.1 Discuss different roles and strenghts at the annual college faculty retreat. | Dean, in consultation with Unit Chairs/Directors C.Anumba (+ M.Kung) | In Progress | 2020-04-08: M.Kung Status
|  | 6.4.2.2 Regularly profile different units, centers, and groups in the college's internal and external communications. | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-16: We work on featuring all the units, centers and groups but are only as good as the information we are given. It is sometimes a struggle to get information. We actually find out a lot through Google Alerts because we aren't notified directly.
| 6.4.3 Provide neutral avenues of conflict resolution and support problem solving. | See Governance - grievance processes. | n/a | -
| 6.4.4 Enhance access to information that is targeted, user-friendly and efficient. | See Governance - college handbook. | n/a | -
| 6.4.5 Enhance communications among staff, units, and faculty. | See Governance - college communications plan. | n/a | -
| 6.4.6 Engage alumni to offer expertise and resources supporting the units as well as keep institutional history alive. | See Governance - alumni relations. | n/a | -
| 6.4.7 Promote mutual respect for all and professional conduct within the College. | See Governance - ethics. | n/a | -
6.5 Promote work-life balance. | 6.5.1 Unit directors inquire with faculty and staff about needs for work-life balance and strategize support that the College can provide. | 6.5.1.1 Form a college committee to explore issues and solutions for work-life balance. | Dean, in consultation with Unit Chairs/Directors and Faculty Council Chair C.Anumba | -
| 6.5.2 Create programs and policies to support work-life balance and advertise existing support available from the university. | 6.5.2.1 Pilot test one program or policy to support work-life balance. | Dean, in consultation with Unit Chairs/Directors and Faculty Council Chair C.Anumba | -
||||||

## 07 Outreach
07. OUTREACH
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Outreach: One of the persistent challenges of our College is that of outreach. As a College, we are dedicated to our teaching and research efforts, and in doing so, may lose sight of the importance of building relationships within and beyond our university community. It is important that we are proactive in engaging the various disciplines, organizations and communities that both support and benefit from our efforts. |  |  | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | In Progress | 2021-10-28: Continuing outreach efforts through Tour Stops, focused private dinner, visits, and social media outlets (STW)
7.1. Reinforce and expand the interactions between the College, its units, its alumni, and the diverse groups that support the activities of the College. | 7.1.1. Reinforce and expand the interactions between the College, its units, its alumni, and the diverse groups that support the activities of the College. | 7.1.1. Establish a “Friends of” program in each academic unit | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | Completed | 2020-02-24: Launched in 2019, yearly mailer
|  | 7.1.2. Identify means for soliciting smaller donations | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | Completed | 2020-02-24: Annual giving for all departments has increased in dollars and donors
|  | 7.1.3. Maximize advisory board contacts | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | Completed | 2021-10-28: All boards have been revamped and are engaged with the development team.
|  | 7.1.4. Send out a call to faculty to provide contact information for potential supporters | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | In Progress | 2021-10-28: On-going effort to get more faculty involved, for example 14 individuals traveled to NYC for Gold Gold Award (STW)
7.2. Establish and enhance connections to the alumni base of the College. | 7.2.1. Establish and enhance connections to the alumni base of the College. | 7.2.1. Increase faculty attendance at alumni events (e.g., DCP Alumni Tailgate and DCP Tour Stops) | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | In Progress | 2021-10-28: Calendar invites sent to all Directors with hopes it will be shared with faculty. However, in some instances space limitations and budget can cause less availablity for attendance. (STW)
|  | 7.2.2. Development team to coordinate with faculty, provide them with a list of alumni contact information and encourage them to communicate/follow-up with alumni | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | Completed | 2020-02-24: UFF Mandates policies and processes
|  | 7.2.3. Develop and disseminate alumni contact guidelines | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | Completed | 2020-02-24: UFF mandates policies and processes
7.3. Expand opportunities for collaborative experiences between units and their respective professional groups while finding additional opportunities for interdisciplinary interaction. | 7.3.1. Expand opportunities for collaborative experiences between units and their respective professional groups while finding additional opportunities for interdisciplinary interaction. | 7.3.1. Increase participation in the DCP Leadership Summit. | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | In Progress | 2021-10-28: On-going effort year to year
|  | 7.3.2. Create a student-led DCP Entrepreneurship program | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | Completed | 2020-02-24: Created in FY19, also supported with endowed gift
7.4. Reconstitute and/or reinforce Program Advisory Boards so they can provide strategic guidance to each academic unit. | 7.4.1. Reconstitute and/or reinforce Program Advisory Boards so they can provide strategic guidance to each academic unit. | 7.4.1. Maximize engagement with advisory board members | Development Team, in consultation with Dean, Unit Chairs/Directors, and Communications Staff S.Watts | In Progress | 2021-10-28: Working with Directors directly to maximize this effort. On-going effort to maximize engagement. (STW)
7.5. Develop a proactive and comprehensive marketing and communication plan that consistently promotes the College’s activities to all stakeholders, the university community, and the wider public. | 7.5.1. Develop a proactive and comprehensive marketing and communication plan that consistently promotes the College’s activities to all stakeholders, the university community, and the wider public. | 7.5.1. Collect information and share/broadcast: Grants awarded, Research publication/outcomes, and Student activities (e.g., exhibits, field trips). | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-08: We are dependent on the units to let us know of these things. Unfortunately, we don't get a lot of the information. Our team (me and Kyle) actively searches out information on this by using Google Alerts and monitoring social media.
|  | 7.5.2. Provide faculty with media training, including social media strategies. | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-16: This is the first I have heard of this but I will start researching how to accomplish this. We have, however, set up social media accounts, held meetings and helped when possible.
|  | 7.5.3. Join UF’s Meltwater account. | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-08: I am meeting with Meltwater on Friday to learn more about their service and pricing. No guarantee we will sign up with them. It's dependent on pricing and what services are offered. Also looking into other services.
|  | 7.5.4. Increase publications in The Conversation (https://theconversation.com/us) | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-08: Recently, we held a tutorial that went over the process of writing for The Conversation. I also attended a webinar hosted by The Conversation that detailed how to pitch them stories. I get regular emails from The Conversation listing stories they are looking for and have pitched several to our faculty.
|  | 7.5.5.Increase the number of faculty on the UF Experts list/website. | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-08: I've sent multiple emails to faculty asking them to apply for the UF Experts site and a handful did. I cannot just put them on the site without their permission. If they don't want to talk to the media, there is no purpose having them on the site.
|  | 7.5.6. Develop and disseminate a list of all social media accounts | DCP Communications Staff J.Mazzaferro | In Progress | 2021-11-09: Kyle is currently getting information for UF Social Media's directory that will promote our account to both internal and external audiences. He requested this from the college's social media managers on 11/2.
|  | 7.5.7. Develop/update media list to enhance media relations | DCP Communications Staff J.Mazzaferro | Completed | 2021-11-08: We've had a media list for several years that we update multiple times a year.
|  | 7.5.8. Redesign the College’s website: 1) Improve consistency by increasing the number of faculty profiles using the profile template. Staff and/or external consultants to distribute the profile template along with instructions for using it. Provide assistance to faculty as required to fully implement the templates college-wide; 2) Update and promote doctoral student pages/profiles; 3) Create a template and process for faculty websites. Assist faculty with creating faculty websites. | DCP Communications Staff J.Mazzaferro | Completed | 2021-11-16: All was completed as assigned. Faculty are all on the website. Ph.D. page was completed but has not been updated in awhile. Eunice is looking over it now. Completed template but faculty have not used it. Up about two years. It has been taken down now.

## 08 Sustainability
08. SUSTAINABILITY
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
Sustainability: It is well understood that the future development and design of our built and natural environments will play an instrumental role in forming and reinforcing the environmental, social and economic health of our communities, cities, nations, and ultimately, the planet. Our College is uniquely positioned to be a leader in providing a clear, positive and ethically sound direction to the underlying issues of why, what and how we build. |  |  | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | -
8.1 Ensure that the College, its faculty and its students actively support ethical conduct and stewardship at all scales of development and geography. | 8.1.1. Evaluate and improve operational sustainability of all college-operated facilities. | 8.1.1.1. Pursue LEED Certification for Operations & Maintenance: Existing Buildings and/or Schools. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | Not Started | 2020-05-18: To optimize the DCP existing buildings performance SBE students in LEED Lab class in fall 2020 will evaluate Rinker Hall performance using LEED V4.1 O+M certification. They will assess the building, apply O+M standards, report findings, and make recommendations for further optimization. The results will be presented to the Dean to consider applying for LEED certification that will cost $3000. Update, this did not happen due to COVID
| 8.1.2. Improve student behaviors with regards to environmental stewardship. | 8.1.2.1. Create and support student-led programs aimed at educating students on ethical conduct and environmental stewardship in their daily life. Engage DCP Ambassadors and student organizations. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | Not Started | 2020-05-18: DCP Ambassadors and members of the USGBC student chapter will be approached this summer (2020) to take the leading role in educating DCP students on sustainability. Meeting will be held with these student groups in early fall 2020 to brain storm and generate a plan on the best approach to accomplish this task. Update, 10-28-21, this did not start due to COVID.
| 8.1.3. Educate students, faculty, and staff on ethical behaviors and environmental stewardship. | 8.1.3.1. Implement annual faculty and staff education sessions. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | Not Started | 2020-05-18: Starting spring 2021 DCP will highlight its accomplishments in advancing environmental stewardship through research, teaching, and services on Earth Day. The SBE Faculty Governing Board will be approached to coordinate and organize this initiative in their June 2020 meeting. Update, 10-28-2021, this did not happen again due to COVID.
8.2 Expand the present interdisciplinary and collaborative problem-solving initiatives regarding the full scope of sustainable development. | 8.2.1. New DCP Collaboratory to be a test platform and living laboratory | 8.2.1.1. Pursue LEED Certification at the highest level possible. Incorporate sensors and performance monitoring tools to allow for ongoing measurement of system/building performance. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | In Progress | 2020-05-18: DCP is planning to integrate sustainability in the planning, design, construction and operation of the addition to Architecture Building (DCP Collaboratory). In addition, we plan to manage/administer LEED process for DCP Collaboratory and use it as a living laboratory for DCP students. Update, 10-28-21, I attened meeting for the DCP's renovation and new construction project meetings. Sustaibility/LEED v4 BD+C Gold certificatio is integrated into the RFP. But, we are not administering the LEED process b/c that is something PDC do, but we can certainly negotiate with them. It is Dr. Chini's call.
| 8.2.2. Increase interdisciplinary research. | Reference 03. "Research" | n/a | -
| 8.2.3. Share ongoing research. | Reference 07. "Outreach" | n/a | -
8.3 Engage industry, government, and non-profits as partners in advancing pedagogical and research strategies. | 8.3.1. Increase engagement with industry, government, and non-profit partners in teaching and research. | 8.3.1.1. Provide support for faculty to pursue funded research opportunities that engage industry, government, and non-profit partners. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | In Progress | 2020-05-18: FIBER will act as a conduit to connect faculty with research and teaching interest in sustainability with industry and government funding agencies. In coordination with the FIBER Director an inventory of DCP faculty with their areas of expertise in sustainability will be created. DCP faculty within that list will be notified when there are funding opportunities in their areas of expertise and possibilities for collaboration. Update, 10-28-21, We met with David Hulse, FIBER conducted a survey, David added "Working with the Dean’s Office staff, in 20/21 FIBER will inventory DCP faculty areas of expertise in sustainability. DCP faculty within that list will be notified by Dean's Office staff when there are funding opportunities in their areas of expertise and possibilities for collaboration with other DCP and/or UF faculty."
|  | 8.3.1.2. Support faculty and student teams pursuing research or service learning that increases external engagements (e.g., Solar Decathlon). | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | Not Started | 2020-05-18: FIBER will Inform DCP students and faculty of the opportunities for student competitions in the area of sustainability and identify a champion that can form and lead a team to participate. Update, 10-28-21 David worked on this "Working with the Director of the Sustainability and Built Environment Program, FIBER will assist in informing DCP faculty of opportunities for student competitions in the area of sustainability to identify a champion that can form and lead a team to participate. When appropriate FIBER may take the lead in organizing and leading such competitions."
| 8.3.2. Support campus developments (outside of DCP) including central plant improvements and new building initiatives. | 8.3.2.1. Collaborate with UF Planning, Design, and Construction staff on new project initiatives. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | In Progress | 2020-05-18: Several units withinDCP collaborate with PDC in using the UF Campus projects as living labs for students, seeking PDC personnel in judging student presentations and mentoring capstone projects, and using the campus building data in research projects. A better approach is to organize these collaboration and sign a MOU with PDC that identifies areas of collaboration related to sustainability. Update, 10-28-21. the MOU drafted but did not go further b/c the Dean asked for funded internship, and he is waiting on VP for Operation to approve. As these process takes long time, and SEB students were in need to gain experiance w/o pay. I notified the Deanand Dr. Chini for the interest of SBE student who are willing to work to gain experiance, I will help SBE students. since last summer, the process is set and working very well. PDC have hierd in position of project engineer last summer one SBE student, had greet feedback from PDC and the student. Fall of 2021, PDC hired 2 other SBe students as interns for 2 consercutive semester. the process is set, we notify our students of the oppertunity, I gather resumes, reviw them, then send them to the PDC Director of Major projects, he interviws students, and offers the position. I check with PDC and the studnets hired regularly to see how all is going so far the feedback from both sides is very good.
8.4 Reinforce curricular structures that are forward-looking and actively address discipline-specific and shared sustainability concerns of the built and natural environments. | 8.4.1. Incorporate ecology + ecological design in coursework | 8.4.1.1. Identify curricular opportunities and review/discuss those with faculty in relevant units. Make recommendations for consideration by facuty units | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | In Progress | 2020-05-18: There are informal collaboration among DCP units in sharing information about multidisciplinary courses in sustainability. The SBE Faculty Advisory Board that has a representative from each DCP unit will identify additional multidisciplinary courses in sustainability and seek volunteers to develop such courses. This collaboration should be expanded to other stainability programs around campus and Office of sustainability. Update, 10-28-21, collaboration between SBE and Interior is strong and moving forward. In fall of 202, both programs offered and co-teaching the first WELL Lab offered golbaly in collaboration with IWBI. the activity involving SBE faculty govening committee did not start due to COVID.
|  | 8.4.1.2. Cross list courses from other units wherever possible. Advertise these opportunties broadly within college and across UF. | Unit Leader of Sustainability and the Built Environment Programs, in consultation with Dean and Associate Dean for Facilities B.Armaghani, in consultation with A.Chini | Not Started | 2020-05-18: It is proposed that the SBE Faculty Advisory Board review curriculum of each unit to identify the existing sustainability courses and recommend developing new multidisciplinary course to be offered at the college level. update, 10-28-21. this task did not start due to COVID.

## 09 International
09. INTERNATIONAL EDUCATION
Goals | Objectives | Enabling Actions (no more than 3-4) | Responsible Person or Group | Status (select from pull-down menu) | Status Notes (50 word maximum)
International Education: The university often references the global reach of The Gator Nation. As a part of the UF academic community, our College has often been noted for its commitments to international education and research. It is critical we reinforce existing efforts and expand our position as global citizens within the international community of scholars and practitioners. |  |  | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | - | 2020-04-08: Most of the objectives will be a continuous process
9.1. Ensure that all interested students and faculty have the opportunity to participate in international travel and educational and research experiences. | 9.1.1. All departments will come up with international programs their students would want to participate in. | 9.1.1.1. Explicitly reference the College’s strategic plan as the basis for college priorities. | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2021-11-18: Most study abroads were canceled during pandemic; slowly starting to resume, dependent on faculty and international partner ¦ 2020-04-08: Exisiting programs exist for all units, but need to be updated periodically.
|  | 9.1.1.2 Establish a mailing list to provide DCP international students with scholarship information and research opportunities | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | Completed | 2020-04-08: Created a listserv for all interested DCP international students and send out appropriate opportunities and information
9.2. Grow the financial support for international travel and education available to students and faculty. |  | 9.2.1.1 Work with development team to establish goals and determine viable partners, appropriate alumni, and local businesses/organizations | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2020-04-08: Combine with section 04 Revenue
|  | 9.2.1.2 Familiarize faculty with funding opportunities available at UF related to international activities | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2020-04-08: Grad School, International Center, and other units across campus often have opportunities.
9.3. Establish consistent linkages with international institutions and increase resources for increased recruitment, retention and graduation of international students at all levels and disciplines. | 9.3.1. DCP will increase international student recruitment and retention efforts | 9.3.1.1. Faculty can work with the department chair/director and Director of Global Education Michael Kung to look into the feasability of establishing a cooperative agreement or joint/combined programs such as a 4+1+1. | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2021-11-18: General MOU agreements can now be signed; joint degree and exchange agreements are still suspended until the General Council and International Center approve a new approval process; priority focus to recruit doctoral and masters students ¦ 2020-04-08: All agreements are currently on hold at UFIC. International cooperation still encouraged, just no agreements can be signed.
|  | 9.3.1.2. Issue periodic surveys to international students to learn about their challenges and needed resources, as well as conduct exit interviews. | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2021-11-18: Listserv has been used to check in with and assist students during pandemic and learn about their challenges ¦ 2020-04-08: Can use the listserv created in 9.1.1.2 to accomplish surveys. Will need to check with IRB.
|  | 9.3.1.3. Develop a communications plan to create a public profile of international activities and generating media interest to attract international students and partners. | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2020-04-08: Most of our international partners/univerisites have a page on international cooperation. Not as common in US.
9.4. Increase student engagement with the international academic community by bringing guest professors and scholars to the College, thereby promoting non-travel based international experience for DCP faculty, staff and students. | 9.4.1. Courses offered by DCP will provide an international speaker opportunity per semester | 9.4.1.1. Encourage faculty to reach out to their contacts and visiting scholars at DCP and invite them to guest lecture/speak to classes (can be done online/electronically to save funds). May also participate in the DCP Research Seminar Series and/or DCP Research Symposium. | Director of Global Education, in consultation with Dean and Unit Chairs/Directors M.Kung | In Progress | 2020-04-08: Visiting scholars are often eager to get involved. Director of Global Education already maintains list of DCP scholars and profiles and has a mailing list for them.
9.5. Encourage future faculty hires that support the international interests and diversity of the College and university. | 9.5.1. International research and teaching experience should be a preferred qualification for all future faculty hires. | 9.5.1.1. International experience is a preferred qualification for all future faculty hires. Depending on the position, search committees to clarify if the experience sought is academic, industry, either, or both. Search committees should post job opportunities on international search sites and review international experiences of applicants as a part of the interview and selection process. | Dean, in consultation with Unit Chairs/Directors C.Anumba | In Progress | 2020-04-08: Confirm with Dean that all Chairs are aware of this qualification. Meet with each unit Chair before new job applications go out.