## Deadline Calculator
College of DCP Countdown to Proposal Submission |  |  | Enter Sponsor Deadline | 2025-09-23
Principal Investigator Deadlines
1 | Utilizing Your Unit's Grant Administrator's Assistance? If Yes, Proceed to #2. If No, Skip to #4. | # of Business Days | Deadline Date | Time
2 | Share Sponsor's Guidelines with your Research Grant Administrator to initiate process Complete UFIRST Smartform and share proposal number: At least 30 Days (Business) prior to DCP Deadline | 35 | 2025-08-05 | 9AM
| If applicable, share the budget cap, Subaward's study team contact with your Research Grant Admin At least 21 Days (Business) prior to DCP Deadline | 26 | 2025-08-18 | 9AM
3 | Draft Proposal Due to your Research Grant Admin (All documents): 14 Days (Business) prior to DCP Deadline | 19 | 2025-08-27 | 9AM
| Final Documents due to your Research Grant Administrator: 7 Days (Business) prior to DCP Deadline | 9 | 2025-09-10 | 9AM
4 | Submit-Ready Proposal: Full and Final Proposal Document Uploaded and Submitted in UFIRST for Department and College Approval 2 Days (Business) prior to Sponsor's Deadline | 2 | 2025-09-19 | 9AM
Research Administrator Deadlines
1 | Assisting Principal Investigators with proposal submission | # of Business Days | Deadline Date | Time
2 | Setup Initial Planning Meeting Review UFIRST smartform, sponsor guidelines, draft and share document checklist, provide templates as needed & collect team Info (if applicable) Within 3 days (Business) of kick-off | 35 | 2025-08-08 | 9AM
| If applicable, contact Subaward team: Provide subaward a checklist of items needed from them along with budget cap and date needed, which should be prior to PI final documents due date. Within 3 days (Business) of receiving | 26 | 2025-08-21 | 9AM
3 | Response to Draft Proposal: Assist with UFIRST budget as needed & provide templates as needed. Within 3 days (Business) of receiving | 19 | 2025-09-01 | 9AM
| Response to Final Documents: Final RA review, assist with sponsor forms (if needed), finalizing documents and attaching final document versions to UFIRST Within 3-business of receiving | 12 | 2025-09-15 | 9AM
4 | Submit-Ready Proposal: Full and Final Proposal Document Uploaded and Submitted in UFIRST for Department and College Approval 2 Days (Business) prior to Sponsor's Deadline | 2 | 2025-09-19 | 9AM
NOTES:
1 | If your sponsor's deadline falls on a Weekend and/or University Holiday, please enter the prior business day as your sponsor's deadline.
PI: If there are any unforseen circumstances or campus closures, please make sure you contact your unit's Grant Admin for submission instructions.
RA: If there are any unforseen circumstances, please make sure to communicate with your PI.
2 | This Calculator does not include University holidays or closings. Be prepared by allowing for expected and unanticipated delays.